## Market Rates
Workstream | Standard Market Low | Standard Market High | Recommended Offer Low | Recommended Offer High | Notes
Strategy / discovery sprint | 85 | 145 | 70 | 115 | Higher because the engagement needs fast scoping and direction lock
UI/UX design and wireframes | 90 | 149 | 70 | 110 | Aligned to boutique design work rather than commodity production
Frontend build / responsive implementation | 60 | 125 | 55 | 95 | Blended from agency dev and senior freelance ranges
CMS / admin dashboard | 75 | 135 | 65 | 105 | Custom editing surface and workflow logic increase complexity
Commerce / integrations | 75 | 150 | 65 | 115 | Stripe, analytics, Mailchimp, and workflow wiring
SEO / analytics implementation | 50 | 100 | 45 | 80 | Technical SEO, GTM, GA4, metadata, and event mapping

## Phase Estimates
Phase | Workstream | Est. Hours Low | Est. Hours High | Market Blended Rate | Offer Blended Rate | Market Range Low | Market Range High | Offer Range Low | Offer Range High
Phase 0 | Style sprint / 3 iterations | 8 | 14 | 110 | 85 | 880 | 1540 | 680 | 1190
Phase 1 | Base launch site + SEO + analytics + storefront | 36 | 52 | 100 | 78 | 3600 | 5200 | 2808 | 4056
Phase 2 | CMS + blog + approval workflow foundation | 48 | 72 | 105 | 82 | 5040 | 7560 | 3936 | 5904
Phase 3 | Affiliate + catalog + advanced integrations | 55 | 88 | 110 | 88 | 6050 | 9680 | 4840 | 7744
[5 empty] | Totals | 15570 | 23980 | 12264 | 18894

## Invoice by Phase
Phase | Deliverable | Qty | Unit | Unit Price | Subtotal | Notes
Phase 0 | Style sprint and 3 visual iterations | 1 | fixed | 950 | 950 | Direction lock only
Phase 1 | Responsive website launch package | 1 | fixed | 4250 | 4250 | Includes SEO base, analytics, storefront
Phase 2 | CMS + blog + approval workflow foundation | 1 | fixed | 6200 | 6200 | Admin, blog, SEO editing, approval gates
Phase 3 | Affiliate + catalog + advanced integration foundation | 1 | fixed | 7900 | 7900 | Future-phase expansion
Optional Retainer | Support / optimization / change requests | 1 | monthly | 1250 | 1250 | Not included in project total
Project Total (Phases 0-3) |  |  |  |  | 19300